Monitoring
-By how much, is it over/under budget?
Budget = 600+1200+400+1200+300=3700
AC=600+1400+200+500=2700
So it is under budget with 1000

-By how many days, is it ahead/behind the schedule?
It is on the time .
-By the end of the project, by how much will it be over/under budget?
600+1400+400+1500+300=4200
4200-3700=500
-Calculate CV, SV, CPI, SPI, EAC

PV = Percent Complete (planned) x Task Budget
EV = Percent Complete (actual) x Task Budget
AC = Actual Cost of the Task
SV = EV – PV
SPI = EV/PV
CV = EV – AC
CPI = EV/AC
EAC = BAC/CPI

	Budget(K)	AC	CV	SV	CPI	SPI	EAC
Preparation	600	600	0	0	1	1	600
Design	1200	1400	-200	200	1.67	0.875	1028.5
Implementation	400	200	200	0	1	1	400
Testing	1200	500	-300	300	1.25	0.8	960
Deployment	300	0	300	-300	1	1	300